## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student. |  |  |  |  | MATTHEW KLUSKA
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 9/5-9/12 | 1) Picked a Project category-> ML/Analytics 2) Picked a project name 3) Picked a tech stack 4) Picked ML and Front end Framework 5) Narrowed down Environment Manager tools to Anaconda/YAML 6) Finalized S_PPP and S_PPP risk management | No Issues as of now | No issues as of now | Start development. Assign technical Tasks to team members. | 12 | 0 | 6 | 6 | 0 | 48 | 45 | 3 | 11.5 | 6 | 3 | 6.5 | 0 | 13 | 5
1
2
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments

## studentName
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05-09/12 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6

## Brendan Truong
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05-09/12 | 6.5 | 5.5 | 1 | 0 - learn git, read on ML 2 - research deployment processes 5 - research assigned document sections, communicate with team 6 - set up git 7 - research similar product | 2 | 1 |  |  |  | 1 | 1 | 0.5 | 1. Write 2 sections of SPPP 2. Set up git, commit a test message on git | 1. not familiar with pytorch, deployment process, or web framework 2. yet to establish concrete tasks | 1. walk through tutorials of pytorch, Elastic Beanstalk for deployment, and Flask 2. meet with team and discuss individual tasks | 0 - learn pytorch, elastic beanstalk, and flask 2 - research and contribute to design of project 3 - run local examples of softwares in task 0 | 15

## Derric Syme
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Configuration leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05-09/12 | 10 | 6.5 | 1.5 | 0 - configure git locally, research CV AI 1 - define high level requirements 3 - Complete required deliverables 5 - Team meetings/communication (Zoom/Discord) 6 - manage team git repo | 1 | 1 |  | 5.5 |  | 2 | 0.5 |  | 1. Write config mangagemnt section of SPPP 2. Confirm git alignment for team 3. Create and perform Iteration 0 presentation 4. Create meeting minutes for first 2 meetings | 1. Some trouble setting up intial git credentials 2. Ambitious project is challenging to plan for 3. Very rusty with cv applications | 1. Set up proper git tokens 2. Project plan will be iterative 3. Reviewed basic documentation | 0 - Continue CV education 1 - continue to define requirements 3 - start to create code 5 - team meetings 6 - maintain updated repo | 8

## Zengrui Luo
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05-09/12 | 5.5 | 3.5 | 2 | 0- learn git and ML 3- complete RiskManagement sheet 5- team meeting 6- setup github | 2 |  |  | 1 |  | 2 | 0.5 |  | 1.write risk management part of SPPP 2.complete RiskManagement sheet 3.setup and commit on git | Task assignment is not very clear. | Assign tasks to each member | 1.learn more about test 2.team meeting | 5.5

## Patounezambo Ouedraogo
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05-09/12 | 7 | 7 | 2.5 | 0 - learning lab1 requirement/git/tutorial 1 - Composing project overview/Non-functional requirements 5 - communications on Discord /and chats/ coordinate work together 7 - Learning deep learning tutorial | 3 | 2 |  |  |  | 1 |  | 1 | 1. Composed/edited SPPP 2. cloned/commited and pushed changes to project repository 3. Wrote progress report | 1. Learning ML/Deep Learning/Computer Vision from scratch 2. Unfamiliar with the Python frameworks FLask and PYthorp | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn ML/Deep learning 1 - work on project requirements 3 - Get to foundational understanding of ML through this project | 7

## Aidan Chang
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Configuration leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/06-09/12 | 9.5 | 7 | 2.5 | 0 - learn lab 1 knowledge 2- project design (front/back-end, ml model) 5 - Team meetings/team files 6 - create git folder for the team, git configurations on local | 0.5 |  | 1 |  |  | 6.5 | 1.5 |  | 1. started a draft for SDD (front/back-end, ml model) 2. Actively articipated all team meetings 3. Contributed to SPPP 4. Started git folders, lab1 branch, and readme.md for team5 | No issues for this week | Learn Flask Learn back-end | 0 - learn Flask and AWS 1 - continue to define requirements 2 - design the API and backend | 10

## MATTHEW KLUSKA
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05-09/12 | 9.5 | 8.5 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 2 | 2 |  |  | 0.5 | 1 |  | 1. Leading project direction( ML service that identifies Cats) 2. Leading technical architecture( Pytorch for model loading, flask for front end, potentially AWS for hosting) 3. Creating stories on pivot tracker and assigning them to leaders. 4. Filling out sections of the SPPP | No issues this week | 1. Knowledge sharing sessions on Flask and Pytorch 2. Create an easy to use wrapper for the ML model 3. Talk with configuration leader about either a .yml or requirements.txt file for the environment set up | 1. Knowledge sharing sessions on Flask and Pytorch 2. Create an easy to use wrapper for the ML model 3. Talk with configuration leader about either a .yml or requirements.txt file for the environment set up | 6