## Sheet1
ZENGRUI LUO
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | some team members drop the class | 2 | 3 | 3 | 36 | team leader | 2022-09-12 | Assign the tasks to other team members. | No one dropped the class so far | Open
| add new team members | new team members join in | 2 | 3 | 3 | 36 | team leader | 2022-09-12 | Assign part of works to new members | No one has been added | Open
| Lack of motivation or responsibility | some team members are not doing their best | 2 | 4 | 4 | 32 | team leader | 2022-09-12 | following the task status. Reassign the task if necessary | No one lack of motivation or responsibility so far | Open
Communication | duplicate work | Some members are doing the same | 1 | 5 | 5 | 5 | team leader | 2022-09-12 | following the task status. Make sure everyone working on their part | no one did duplicate work | open
| worked on wrong components | Some members work on others job | 2 | 4 | 4 | 16 | team leader | 2022-09-12 | following the task status. Make sure everyone working one their part | no one work on others part | open
| useless work | Some members did unnecessary work | 2 | 4 | 4 | 16 | team leader | 2022-09-12 | following the task status. Make sure everyone working right task | no one did useless work so far | open
| inconsistent work | some members not well coporated with others | 2 | 4 | 4 | 16 | team leader | 2022-09-12 | following the task status. Make sure everyone work consistantly | no one work inconsistantly | open
Requirements | unclear requirements | unclear requirements | 2 | 5 | 5 | 20 | Requirements Leader | 2022-09-12 | clear requirements | no unclear requirement so far | open
| scope creep | unnecessary or too much requirement | 2 | 5 | 5 | 20 | Requirements Leader | 2022-09-12 | delete unnecessary requirement | no scope creep so far | open
| constant requirements changes | always change requirements | 3 | 5 | 5 | 15 | Requirements Leader | 2022-09-12 | clear requirements | no constant requirements changes | open
Management | improper task assignments | assigned task to imporper members | 3 | 5 | 5 | 15 | team leader | 2022-09-12 | Assign tasks based on each member's strengths | no improper task assignments | open
| improper planning | didn't well plan the deadline of each step | 3 | 5 | 5 | 15 | team leader | 2022-09-12 | plan the deadline of each step | no improper planning | open
| lack of management skills | lack of management skills | 3 | 5 | 5 | 15 | team leader | 2022-09-12 | make sure every member understand their task and deadline | everything good | open
Technology competence | Not familiar with the framework used | not clear how to use the framework | 2 | 5 | 5 | 20 | Design and Implementation leader/QA leader | 2022-09-12 | meet or discuss with members who familiar with the framework | members are familiar with the frameworks | open
| Not familiar with the programming language used | members not good at the programming language used | 1 | 4 | 4 | 40 | Design and Implementation leader/QA leader | 2022-09-12 | meet or discuss with members who familiar with the language | members are good at python | open
| Not familiar with unit testing | members not familiar with unit testing | 2 | 4 | 4 | 32 | security leader/QA leader | 2022-09-12 | meet or discuss with members who familiar with unit testing | everything good so far | open
| Other technology incompetence | Other technology incompetence | 3 | 3 | 3 | 27 | QA leader | 2022-09-12 | meet and discuss | no other technology incompetence yet | open
| Not familiar with Git | members don't know how to use git | 1 | 1 | 5 | 125 | Configuration leader/All members | 2022-09-12 | ask other members or google | everyone know how to use git | open
Design and implementation | Improper design | Design does not meet requirements | 2 | 4 | 4 | 32 | Design and Implementation leader/ Requirements leader/QA leader | 2022-09-12 | Make sure the design meets all requirements | no improper design so far | open
| improper technology stack | improper technology stack | 2 | 4 | 4 | 32 | All member | 2022-09-12 | adjust the technology stack | everything good | open
| Messy code | duolicate or useless code exist | 2 | 5 | 5 | 75 | All member | 2022-09-12 | check the code and remove the duplicate part | no messy code yet | open
Testing | Not enough testing | lack of testcases or coverage is too low | 2 | 4 | 4 | 32 | security leader/QA leader | 2022-09-12 | write more testcase to improve test coverage | no testcases needed yet | open
Integration and deployment | Not enough time for integration and deployment | didn't schedule time for integration and deployment | 2 | 4 | 4 | 32 | team leader/Configuration leader | 2022-09-12 | schedule the deadline of tasks and make sure the time for integration and deployment | everything good | open
The team member who is adding the new feature should be the one who determines what is correct for the new functionality that was added.
Work together as a team to make sure each developer has the same environment. This is useful so that there aren't accidental bugs added due to environment issues.